## Sheet1
Module | Phase | Task | Description | Status | Effort (Days)
Threat Library | Initiation Phase
|  | Project Kickoff | Define project objectives, scope, stakeholders, and communication channels. | WIP | 5
|  | Stakeholder Identification | Identify key project stakeholders and their roles; create a stakeholder communication plan. | WIP | 2
| Planning Phase | Define Scope and Objectives | Document the specific scope and objectives of the threat library; define success criteria. | WIP | 10
|  | Resource Planning | Allocate human and technical resources; develop a resource management plan. | WIP | 5
|  | Create Project Schedule | Develop a detailed project schedule with milestones and dependencies. | WIP | 10
Execution Phase
Platform Selection
|  | Identify Requirements | Determine specific platform/tool requirements based on project needs. | WIP | 5
|  | Proof of Concept (POC) | Conduct a POC to test platform/tool functionality and compatibility. | Completed | 10
|  | Procurement | Initiate procurement process for acquiring the selected platform/tool. | Yet to Start | 5
Taxonomy Development
|  | Category Definition | Define high-level threat categories and subcategories. | Yet to Start | 7
|  | Taxonomy Documentation | Create detailed documentation of taxonomy structure and guidelines. | Yet to Start | 10
|  | Review and Validation | Review taxonomy with stakeholders for feedback and validation. | Yet to Start | 5
Data Collection
|  | Data Sources Identification | Identify potential sources of threat intelligence data. | WIP | 5
|  | Data Feeds Integration | Establish Mechanissm to link threats with CAPEC ,CWE and and mechanisms for collecting data feeds. | WIP | 7
|  | Threat Library Development | Development of Threat Library for 200 components | WIP | 200
|  | Data Ingestion | Implement processes for ingesting and storing threat data securely. | Yet to Start | 8
Threat Documentation
|  | Template Design | Design a standardized threat documentation template. | Yet to Start | 5
|  | Data Entry | Begin entering known threats into the library using the template. | Yet to Start | 14
|  | Quality Assurance | Implement quality control processes to ensure accuracy and consistency. | Yet to Start | 7
Risk Assessment
|  | Risk Scoring Criteria | Define criteria and methodology for assigning risk scores to threats. | Yet to Start | 7
|  | Risk Assessment Process | Start assessing threats based on established criteria and record scores. | Yet to Start | 14
|  | Risk Review | Periodically review and update risk assessments as new data becomes available. | Yet to Start | 7
Version Control Setup
|  | Version Control System Selection | Choose a suitable version control system or software. | Yet to Start | 5
|  | Repository Creation | Create a dedicated repository for storing threat library data. | Yet to Start | 7
|  | Access Control | Implement access controls and permissions for version control. | Yet to Start | 7
Access Control Implementation
|  | User Roles and Permissions | Define user roles and set permissions (e.g., read-only, editor, admin). | Yet to Start | 7
|  | Role Assignments | Assign team members to their respective roles. | Yet to Start | 5
|  | Testing Access Controls | Conduct testing to ensure access controls function correctly. | Yet to Start | 7
Integration with Tools
|  | Integration Development | Develop connectors/APIs for data exchange between the library and tools. |  | 14
|  | Testing and Validation | Test integrations to verify data accuracy and consistency. |  | 10
| Monitoring and Control Phase |  |  | Yet to Start
|  | Regular Updates | Develop a process for regularly updating the threat library with new threats and vulnerabilities. | Yet to Start | 14
|  | Metadata and Context | Include metadata to provide context for each threat, such as discovery date and attribution. | Yet to Start | 10
|  | Training and Awareness | Train relevant personnel on how to use the threat library effectively; conduct awareness programs. | Yet to Start | 10
| Closure Phase |  |  | Yet to Start
|  | Testing and Validation | Test the threat library for accuracy and completeness; validate its effectiveness. | Yet to Start | 14
|  | Feedback Mechanism | Establish a feedback mechanism for users to report new threats or suggest improvements. | Yet to Start | 7
|  | Documentation and Reporting | Create documentation on how to use the threat library effectively; generate reports for management and incident response. | Yet to Start | 14
Threat Library AI Model Development | Planning Phase |  |  | Yet to Start
|  | Define Scope and Objectives | Clearly define the scope of the AI LLM model and its objectives in automating threat library creation. | Yet to Start | 10
|  | Resource Planning | Allocate human resources, data sources, and computing resources required for model development. | Yet to Start | 10
|  | Risk Assessment and Mitigation | Identify potential risks in model development, assess impact and likelihood, and develop mitigation plans. | Yet to Start | 7
|  | Data Collection Strategy | Plan the strategy for collecting software asset data and threat intelligence feeds. | Yet to Start | 14
|  | Project Schedule | Develop a detailed project schedule with milestones and dependencies for model development. | Yet to Start | 10
| Execution Phase |  |  | Yet to Start
|  | Data Collection | Implement the data collection strategy to gather information on software assets and threat intelligence. | Yet to Start | 20
|  | Model Architecture Design | Design the architecture of the AI LLM model for threat library creation. | Yet to Start | 14
|  | Data Preprocessing | Prepare and clean the collected data for training the model. | Yet to Start | 10
|  | Model Development | Develop and train the AI LLM model using appropriate machine learning techniques. | Yet to Start | 30
|  | Threat Library Creation | Utilize the model to automatically generate a threat library for software assets. | Yet to Start | 20
|  | Quality Assurance and Testing | Test the accuracy and completeness of the generated threat library; refine the model as needed. | Yet to Start | 14
| Monitoring and Control Phase |  |  | Yet to Start
|  | Model Validation and Fine-Tuning | Validate the model's performance with cybersecurity experts and fine-tune it based on feedback. | Yet to Start | 14
|  | Integration with Asset Management Systems | Integrate the threat library with existing software asset management systems. | Yet to Start | 10
|  | Documentation and Training | Document the model's architecture and usage instructions; provide training | Yet to Start | 10
| Closure Phase |  |  | Yet to Start
|  | Testing and Validation | Conduct final testing and validation of the AI LLM model and the integrated threat library. | Yet to Start | 14
|  | Project Closure | Formalize the project closure, including documentation handover and project archive. | Yet to Start | 5